## Group member 1
Name - Corey Angel Almonte
Revised Deadline: 2/14 | Date - 2/14/2025 |  |  |  | To be completed by: |  | 2025-02-14 |  | Name Zhian Maysoon
[5 empty] | Deadline: |  | 2025-02-14 |  | Date 02/14/2025
Original Due By | Revised Due By | Number Of Days | Revision Notes |  | Project 1
2025-02-03 |  | 1 |  |  | % done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
2025-02-14 |  | 11 |  |  | 100% | Planning Assignment with group members | 2025-02-10 | 2025-02-10 | 2025-02-10
2025-02-14 |  | 6 |  |  | 75% | Queries and textbook exercises | 2025-02-13 | 2025-02-11 | 2025-02-13
2025-02-14 |  | 6 |  |  | 50% | Notebook & presentation script | 2025-02-13 | 2025-02-12 | 2025-02-13
2025-02-14 |  | 6 |  |  | 25% | Recording Presentation Video | 2025-02-14 | 2025-02-13 | 2025-02-14
2025-02-14 | 2025-02-14 | 1 |  |  | 0% | Refining Video & documentation | 2025-02-14 | 2025-02-14 | 2025-02-14
[5 empty] | 0% | Final review and submission | 2025-02-14 | 2025-02-14 | 2025-02-14
Name - Mark Cappuccio-Baer
Revised Deadline: 2/14 | Date - 2/14/2025
Original Due By | Revised Due By | Number Of Days | Revision Notes
2025-02-03 |  | 2
2025-02-08 |  | 6
2025-02-09 |  | 2
2025-02-10 |  | 2
2025-02-10 |  | 1
2025-02-11 | 2025-02-14 | 1
February 14th, 2025 | Name: Bryan C. Weng Jiang
February 14th, 2025 | Date: February 14th, 2025
ORIGINALLY DUE BY | REVISION DUE BY | NUMBER OF DAYS | REVISION NOTES
February 3rd, 2025 |  | 2 Days (Without Revision)
February 7th, 2025 |  | 5 Days (Without Revision)
February 9th, 2025 | February 14th, 2025 | 3 Days + 5 (With Revision)
February 9th, 2025 | February 14th, 2025 | 1 Day + 5 (With Revision)
February 10th, 2025 | February 14th, 2025 | 1 Day + 4 (With Revision)
February 12th, 2025 | February 14th, 2025 | 2 Days + 2 (With Revision)
NAME | SABIR AHAMED
To-do list
| To be completed by: |  | 2025-02-14 |  | Sabir ahamed
| Deadline: |  | 2025-02-11 | Revised Deadline: 2/14 | Date - 2/14/2025
Project 1
| % done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
| 100% | Planning Assignment with group members | 2025-02-04 | 2025-02-05 |  | 2
| 100% | Queries and textbook exercises | 2025-02-06 | 2025-02-08 |  | 2
| 100% | Notebook & presentation script | 2025-02-08 | 2025-02-09 |  | 1
| 100% | Recording Presentation Video | 2025-02-09 | 2025-02-10 |  | 2
| 100% | Refining Video & documentation | 2025-02-12 | 2025-02-13 |  | 1
| 100% | Final review and submission | 2025-02-14 | 2025-02-14 |  | 1

## Group member 2
To-do list
To be completed by: |  | 2025-02-14 |  | Name Zhian Maysoon
Deadline: |  | 2025-02-14 |  | Date 02/14/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning Assignment with group members | 2025-02-10 | 2025-02-10 | 2025-02-10
75% | Queries and textbook exercises | 2025-02-13 | 2025-02-11 | 2025-02-13
50% | Notebook & presentation script | 2025-02-13 | 2025-02-12 | 2025-02-13
25% | Recording Presentation Video | 2025-02-14 | 2025-02-13 | 2025-02-14
0% | Refining Video & documentation | 2025-02-14 | 2025-02-14 | 2025-02-14
0% | Final review and submission | 2025-02-14 | 2025-02-14 | 2025-02-14

## Group member 3
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 4
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up