## Project Planner
ASSIGNMENT II PLANNER
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | Percentage Complete |  |  |  |  | Actual (Beyond Plan) | [7 empty] | Percentage Complete (Beyond Plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS |  |  | MEMBERS OF GROUP 3: Sabir Ahamed, Redhwan Ahmed, Corey Almonte, Mark Cappuccio-Baer, Farhan Ekka, Zhian Maysoon, Edwin Paucar, Bryan Weng Jiang
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Planning Assignment With Group Members | 2 | 6 | 2 | 5 | 100%
Queries And Textbook Exercises | 3 | 7 | 3 | 5 | 100%
Notebook And Presentation Script | 7 | 3 | 6 | 7 | 100%
Recording Presentation Video | 9 | 1 | 6 | 6 | 100%
Refining Video And Documentation | 5 | 1 | 5 | 5 | 100%
Final Review And Submission | 6 | 2 | 1 | 4 | 100%