## Sheet1
To-do list
To be completed by: |  | 2025-04-07 |  | Name -Sabir Ahamed
Deadline: |  | 2025-04-08 |  | Date 04-04-25
HW8
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning assignment | 2025-04-04 | 2025-04-05 |  | 1
100% | Queries and textbook exercises | 2025-04-05 | 2025-04-06 |  | 1
100% | Notebook & presentation script | 2025-04-05 | 2025-04-07 |  | 3
100% | Recording | 2025-04-08 | 2025-04-08 |  | 1
100% | Refining video & documentation | 2025-04-08 | 2025-04-08 |  | 1
100% | Review/submit to homework leader | 2025-04-09 | 2025-04-09 |  | 1